*April 2013*

Monthly Technical Status Report

Subcontract Name: *caGrid Enhancement*

Subcontract #: *12ST1112*

Subcontractor: *Inventrio*

Submitted By: *John Eisenschmidt*

Date Submitted: *May 10, 2013*

# 

# Project Background/Objectives

1. Software Development to replace the Globus Axis stack with the WS\* and WS-Security and WS-Trust elements and to migrate to the SHA-2 Infrastructure,
2. Software Development to make registering a new service on caGrid much easier
3. Operations and Maintenance of the existing software components.
4. Support the migration of the Training Grid from its current location to the NCI production environment
5. Support the migration of cagrid.org to the NCI wiki or NCI defined location
6. Support migration of code, issues, and documentation to an open source repository defined by the NCI

# Technical Overview

* WS\* - Explore moving to caGrid 2.0 technology stack
* Security enhancements to support SHA2 and WS-Security
* Migration of svn repositories to github
* Operations and Maintenance of caGrid 1.4 release

# Personnel Roster

Below is a list of team members supporting each subproject.

| **Subproject(s)** | **Name** | **Title / Role** |
| --- | --- | --- |
|  | John Eisenschmidt | Project Manager |
|  | Steve Langella | Software Architect |
|  | Scott Oster | Software Architect |
|  | Shannon Hastings | Software Architect |
| Development | Dave Heisterberg | Software Developer |
| Training Grid, caGrid.org | Justin Kuss | Software Developer |
| Training Grid, caGrid.org | Ryan Naylor | Software Developer |

Personnel Changes

Will Ryan left Inventrio 4/12/13

# Current Technical Status

## Description of Technical Status

Prototype development of caGrid 2.0 services that are backwards compatible to caGrid 1.4. Instantiating Training Grid to replace OSU instance.

## Completed Activities

Below is a list of activities completed this month for each subproject.

| **Subproject(s)** | **Activity** | **Description** |
| --- | --- | --- |
| **caGrid.org** | Migration of caGrid.org from OSU to NCI | April 13, 2013 |
| **Training Grid** | Migration of Training Grid from OSU to NCI | April 13, 2013 |

# Next Month Plans

## Description of Plans

* Finalize prototype caGrid 1.4/WSRF service in caGrid 2.0 tech stack
* Complete OSDI migration from svn to Github and conduct close-out meeting

## Planned Activities

Below is a list of activities planned for next month for each subproject.

| **Subproject(s)** | **Activity** | **Description** |
| --- | --- | --- |
| Development | Finalize prototype caGrid 1.4/WSRF service in caGrid 2.0 tech stack |  |
| OSDI | Complete OSDI migration from svn to Github | Close-out meeting |
| JIRA | Project Communication | Move Inventrio JIRA tasks to NCI JIRA Project |

# Schedule management

## Milestones

| **Subproject(s)** | **Milestone** | **Delivery Date** | **Status** |
| --- | --- | --- | --- |
| **Development** |  |  | Elaboration |
| **OSDI** | Migration from NCI svi to Github | May 15th | Close-out meeting |
| **JIRA Migration** | Migrate Inventrio’s caGrid JIRA project to NCI JIRA | TBD | Assessment |

## dependencies

| **Subproject(s)** | **Dependency** | **Date** | **Status** |
| --- | --- | --- | --- |
|  |  |  |  |
|  |  |  |  |

## deliverables

| **Subproject(s)** | **Deliverable Name** | **Deliverable Location** | **Due Date** | **Date Updated** | **Status** |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |

# Communications Management

Below is a list of meetings attended this month for each subproject.

| **Subproject(s)** | **Topic** | **Date** | **Project Attendees / Link (Optional)** |
| --- | --- | --- | --- |
|  | caGrid Weekly Meeting | April 5, 12, 19, 26 | John Eisenschmidt, Steve Langella, Scott Oster, Shannon Hasting |
| OSDI | OSDI Daily Standup | April 1,3, 5, 8, 10, 12, 15, 17, 19, 22, 29 2013 | John Eisenschmidt, Scott Oster, Justin Kuss, Will Ryan |

# Issue Management

| **ID** | **Subproject(s)** | **Description** | **Owner** | **Actions** | **Priority (H, M, L)** | **Status (Open, Closed)** |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | None |  |  |  |  |

# Risk Management

| **ID** | **Subproject(s)** | **Description** | **Owner** | **Potential Impact (H, M, L)** | **Mitigation/ Status** | **Priority (H, M, L)** | **Status (Open, Closed)** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | **Training Grid** | Hardware Security Module | Steve Langella | H | Resolved |  | Closed |
| 2 | **SHA-2** | Hardware Security Module | Steve Langella | H | New | H | Open |